## Slide 1: Module 6 - Planning community conservation interventions and projects
Uganda Wildlife Authority
Community Conservation Wardens
Training Pack: 2018 & 2019

## Slide 2
This module is part of the UWA Community Conservation Warden training package, which was designed for UWA, with support from IIED and funding from UK Aid. The package contains the following modules:
Introduction to Community Conservation
Effective Communication
Community Mobilisation
Facilitating Community Meetings
Undertaking Gender Assessments for Conservation
Planning Community Conservation Interventions and Projects
Conflict Management
Monitoring & Evaluation Reporting
All modules can be found via www.iied.org/UWA-warden-training

## Slide 3: Module 6: Planning a Community Conservation Intervention
1. Basic terminology in conservation interventions and projects
Learning objective: Understand terminology
2. Planning
Learning objective: Learn about the steps of planning for a conservation project or intervention
Note: this module focuses on the core elements of the planning process: for details on budgeting, and on monitoring and evaluation, please refer to Bibby and Adler 2008

## Slide 4: 1. Basic terminology in conservation intervention and Project
Learning objective 1: Understand basic terminology in conservation intervention and project planning

## Slide 5
Project
Intervention
Community project
Planning
Concepts and definitions

## Slide 6
‘A series of activities aimed at bringing about clearly specified objectives within a defined period and with a defined budget’
  Clearly identified stakeholders and target beneficiaries
  Defined management and financing arrangements
  A monitoring and evaluation system
  European Commission, 2004: 8
‘A project is a group of interrelated activities and results with a unified purpose, together with the resources and time frame to achieve them’
  Bibby and Alder 2003: 4
Project

## Slide 7
An intervention is a mechanism or tool for solving a ‘problem’; interventions can constitute the different elements of a project
  An intervention may include educational programmes, new or stronger policies, or a promotional campaign
  In conservation, interventions usually focus on behavioural change
Intervention
ICRC 2008: 19

## Slide 8
Community project refers to actions planned and undertaken by a community in response to a collaborative decision to make a change or an improvement
  Characterised by a high degree of participation and engagement (see Module 3: Community Mobilisation)
Community project

## Slide 9
“Planning is about informed decisions based on structured and logical thinking about the future, which resources are required, and working out how you will know whether you have achieved your objectives”
  Planning is a means to an end, not an end in itself
  You need to be flexible and adjust your plan as you work
Planning
Bibby and Adler 2003

## Slide 10: 2. Planning
Learning objective 2: Learn about the steps of planning for a conservation project or intervention
NB: the focus here is on projects but the principles apply to planning an intervention

## Slide 11
“Project planning is a process of structured and logical thinking, in which the overall aim is to co-ordinate decisions that will influence, direct and control the future and help to achieve the project objectives” - Bibby and Adler 2003
Project planning

## Slide 12
Consider the following scenarios
  An organisation contacts you asking for US$100,000 to conserve a forest that is a wildlife corridor for elephants from your park to another protected area
  An community conservation warden wants US$5,000 from HQ to do ‘important community work’ to save a threatened bird species around a protected area
Would you give them the money?
How would you make your decision?
Brainstorm: why plan?
Bibby and Adler 2003

## Slide 13
You will need more information before you decide to allocate any amount of money, large or small
What do you need to know to make your decision?
  How important the forest area or threatened bird is
  What kind of problems or conflicts there are at the sites
  What they want to spend the money on
  Whether the organisation or community conservation warden is capable of doing the job
  Whether the project proposed requires a smaller or bigger budget than the one asked for
Brainstorm: why plan?
Bibby and Adler 2003

## Slide 14
You would be concerned if you found out that the money was going to be used for conserving a site already designated for logging and where the applicant for funds had no ability to influence this
Equally as worrying would be finding out that local people are opposed to the project because it would fence off an important grazing area
Planning helps you to identify possible problems and obstacles in advance! There are certain questions you can ask and tools you can use to assist you in planning effectively
Brainstorm: why plan?
Bibby and Adler 2003

## Slide 15
Whatever your approach, there are some key elements to project planning. Think of planning as a structured way to answer fundamental questions of any project:
Why do we need a project? (problem and stakeholder analysis)
What are we trying to achieve? (goals and objectives)
How are we going to achieve our objectives? (project strategy)
What do we need to achieve our objectives? (inputs and resources)
How will we know when we have reached our goal(s)? (indicators, monitoring and evaluation)
Who is doing what? (roles and responsibilities)
Planning: key elements
Bibby and Adler 2003

## Slide 16
Principles of a good project plan
A clear statement of the overall objective
A set of realistic sub-goals focusing on the overall goal
A set of indicators for monitoring and evaluating progress towards objective(s)
Use of best information and lessons learnt from past projects
Involvement of stakeholders and beneficiaries
Flexibility of approach
Comprehensive grasp of all aspects of the issue at hand
Identification of key external and internal influencing factors
Shared understanding of the plan from all those involved
Bibby and Adler 2003

## Slide 17
In practice, your approach will probably be somewhere between the two extremes. For more detail on the advantages and disadvantages of these approaches, see Adler and Bibby 2008, p35
Two approaches to planning:
Top down | Bottom up or participatory
Plans are formulated by management and then passed down for implementation | Plans are produced involving active participation of stakeholders
Often used for large-scale development plans or to define the strategic orientation of organisations | Generally used for specific community projects where the participation of local people is crucial for project success
Based on a number of specialists who agree priorities (such as globally threatened species) and set high level objectives and targets | 

## Slide 18
Sharing stories: building a wall of success (15 minutes)
In groups:
A participant describes a successful project he/she has implemented with community members, including information about their role in the process, and lessons learnt
Another participant describes a project that did not work, including information on their role in the process, and lessons learnt
Group work: principles and skills in project planning

## Slide 19
Planning Step 1: Ideas
This is about deciding what needs to be done, based on ideas of a desired situation
E.g. there is illegal cutting of trees in Kibera sector of the park. You want to control or stop this activity
Ideas of a desired situation
  You’ll have good results if there is regulated access to trees inside the park
  You’ll have even better results if people have access to trees outside the park
  You’ll have even better results if the two activities are combined

## Slide 20
Planning Step 1: Ideas
Thinking about your desired situation
  What behaviour needs to change?
  Whose behaviour needs to change?
  How can people be helped or allowed to change their behaviour?
What changes need to happen as a direct result of the project(s)?
  In this case, little or no cutting of trees in the park
Participatory methods might be useful to identify the issues and how local people define the problem e.g. focus groups or other workshop activities

## Slide 21
Planning Step 2: Stakeholder analysis
We need to know the stakeholders because these are people who can influence the success of your project, and who can inform it. Think especially about the following:
Targets of change
  people whose behaviour you are trying to change
  may or may not be the same people who will benefit from the project
Agents of change
  people who can make change occur
  Could be leaders, or community role models

## Slide 22
Planning Step 2: Stakeholder analysis
Stakeholder analysis can involve a combination of CCW knowledge and participatory approaches – for example, the CCWs can brainstorm the most obvious stakeholders, then use interviews/focus groups/surveys to uncover the less obvious stakeholders. It is important not to forget any vulnerable groups (Schneider 2016)
  Stakeholder identification is an iterative process; see Module 7: Conflict Management for more details on stakeholder analysis tools, and Module 5: Undertaking Gender Assessments for Conservation for a reminder of why gender analysis is important!

## Slide 23
Planning Step 2: Stakeholder analysis
Who are the stakeholders in the case of illegal cutting of trees in the park?
  Charcoal burners
  Pitsawyers
  People constructing homes
  Women collecting firewood
  People trading firewood
  Local politicians and leaders

## Slide 24
Planning Step 3: Problem analysis
In this step the objective is to understand the situation the project intends to address. There are various methods that can be used to help you understand the problem at hand:
Community assessment and problem identification (participatory methods)
Problem analysis
Problem tree
  See Module 7: Conflict Management for more details on the above problem analysis tools

## Slide 25
Planning Step 3: Problem analysis
How to think about your problem:
Ensure that you identify real, existing problems
Don’t become preoccupied with defining a ‘core’ problem from the very beginning; this will become clearer through later discussion
When defining a problem try not to do it in terms of ‘lack’ ie a problem is not a lack of a solution, but rather an existing unwanted situation (Bibby and Alder 2008)

## Slide 26
Planning Step 3: Problem analysis
Writing a clear and concise problem statement is necessary before moving onto Step 4 – it will guide all further steps!
Elements of a good problem statement:
  Description, quantitative and qualitative, of the problem
  Stakeholder impacts, described quantitatively and qualitatively (who and how many)
  Concise explanation of causes and impacts of the problem

## Slide 27
Planning Step 3: Problem analysis
Example of a problem statement
“Clearance of woodlands for firewood and cash-crop farming has left the valley with only 10% of its original forest cover. Fourteen restricted range birds occur in these forests of which three are globally threatened. Continuing clearance is increasing the isolation of surviving forest fragments, which may render populations of the least dispersive species non-viable. Some 40 families live on smallholdings in the valley and make their income from cash-crops. A thriving eco-tourism business on the lower slopes rarely brings visitors to the forest because the area is difficult to access from the nearest tourist accommodation 50 kilometres away. Local people may have a very low per capita income and continued forest clearance provides the only option they currently have available to supplement this. The total loss of these forests would be a major loss to biodiversity, not only in terms of birds, but probably other taxa too.”
Bibby and Adler 2003

## Slide 28: Group activity: brainstorm
What could be another unwanted situation in Bugote sector of the park?
Example of illegal tree cutting in Kibira National Park
‘Reduced sighting of Crowned Cranes in Bugote sector of the park near Bushura parish because of intensive tree cutting.......’

## Slide 29
Planning Step 4: Stakeholder involvement
Involve stakeholders of the project and potential clients depending on what the issues/problems are
This is the point to make sure all your identified stakeholders are involved, engaged, and able to give their input
Don’t assume you already know what they want – use tools such as PINs analysis – see Module 7: Conflict Management
Encourage people to ‘take ownership’ – see Module 3: Community Mobilisation

## Slide 30
Planning Step 4: Stakeholder involvement
How to involve stakeholders
Informal personal contact
Interviews
Focus groups

## Slide 31
Planning Step 5: Set goals and objectives
“Objectives are statements of how you want the world to look when you have fixed a particular problem”, Adler and Bibby 2008; 50
Answer the following questions as concretely as possible:
What should the project accomplish? GOAL
What will success look like? OUTCOMES
How will you explain to other people that the project has worked? OUTPUTS
What are the benchmarks you will use to show you are moving in the right direction? INDICATORS

## Slide 32
Planning Step 5: Set goals and objectives
Hierarchy of project objectives:
One overall project goal
One overall project purpose
Approximately 4-10 results
Approximately 4-10 activities per result
You may wish to use a log-frame (logical framework) to plan your project’s goal, purpose, results and corresponding activities. For more details on using log-frames, refer to Adler and Bibby 2008, Section 3.6

## Slide 33
Planning Step 5: Set goals and objectives
SMART objectives
Each objective needs to be a single sentence statement describing a desired future state. Use SMART to keep you focused. SMART objectives should be:
Specific
Measurable
Achievable
Realistic
Timebound
Bibby and Adler 2003

## Slide 34
Planning Step 6: Identify the specific project
This is where you look at your objectives as per Step 5, and work out what should be done to achieve them
Note: You can use an evidence-based model for planning your project. This means using data on outcomes of previous similar project to inform your objectives, helping you to think about what may and may not work in your context (see Baker et al 2015)

## Slide 35
Planning Step 7: Risk Assessment and mitigation
Identify barriers and resistance you might come up against
What barriers and resistance might you face? How can they be overcome? Be prepared for whatever may come your way!
For example:
Pitsawyers and timber dealers may resist the project
What are suitable tree species for planting (termites, food security, acceptance)
Appropriate income generating projects; e.g. if community is predominantly Muslim, you may not promote piggery projects
Gender issues, land ownership, land tenure

## Slide 36
Planning Step 8: Develop a strategy
Taking into account your identified objectives and desired results from Step 5, your chosen project from Step 6, and your risks from Step 7, you can now develop your strategy – the ‘big idea’ approach that will then be broken down into specific activities
Examples:
Raise awareness and sensitisation of target community about the dangers of uncontrolled tree cutting from the park
Provide alternative sources of income to the poor households and people directly engaged in tree cutting from the park for domestic or commercial purpose

## Slide 37
Planning Step 9: Develop an action plan to implement the project
This is where you identify who will do what activities, when, and with what resources to support them.
What components and elements will be implemented?
Who should implement what by when?
What resources and support are needed? What is available?
What potential barriers or resistance are expected? How will they be minimised?
What individuals or organisations need to be informed? What do you need to tell them?

## Slide 38
Planning Step 9: Develop an action plan to undertake the project
Example
Activity | Objective | Time Frame | Responsible person | Where | Beneficiaries (who and number) | Funding | What should other partners do | What should communities do | Funding | 
 |  |  |  |  |  |  |  |  | Source | Amount

## Slide 39
Planning Step 10: Implement your project
If you have followed all the steps, implementation will be made easier. Consider piloting your activities; remember to budget for this!
Be adaptable and flexible; as conditions change, so should your strategy!

## Slide 40: To sum up....
Planning takes time but it is absolutely crucial
Follow all the steps methodically – BUT remember to remain flexible and adaptable where necessary! As your situation changes, so should your plan
Refer to all the previous training modules – all those skills are necessary for successful project planning and implementation!

## Slide 41
Turn to the Work Plan in your training manual and think about your key learning from today, and how you might apply it in practice!
Don’t forget!

## Slide 42: Acknowledgement
These modules were developed and administered by Mrs Eunice Duli and Mrs Agripinnah Namara

## Slide 43: Thank you
This training is part of the project: Implementing park action plans for community engagement to tackle IWT, coordinated by IIED and grant funded by the UK government’s Illegal Wildlife Trade (IWT) Challenge Fund.
The IWT Challenge Fund is for projects around the world tackling illegal wildlife trade and supports action in three areas, including developing sustainable livelihoods for communities affected by illegal wildlife trade. The views expressed are not necessarily the views of the UK government.

## Slide 44: References
Bibby C. J. and Alder, C. (eds), 2003, The Conservation Project Manual, BP Conservation Programme, Cambridge UK https://www.icrc.org/en/doc/assets/files/publications/icrc-001-0951.pdf
Baker J. et. al., (2015), Fairer, better. A guide to more effective Integrated Conservation and Development in Uganda, IIED. UK. https://pubs.iied.org/14649IIED/
Schneider et al 2016, INTRINSIC: Integrating Rights and Social Issues in Conservation (A Trainer’s Guide), http://www.cambridgeconservation.org/resource/toolkits/intrinsic-integrating-rights-and-social-issues-conservation-trainers-guide